| Project ID | PJ001142 |
| --- | --- |
| Project Fiscal Year | 2024-2025 |
| College/Department/Unit | College of Agriculture/SPESS |
| Title of Project | Step Up the Water - Enhancing Student Learning through Two Innovative Water Systems |
| Name of Principle Implementor | Dr. Yan Chen |
| Email | yachen@agcenter.lsu.edu |
| Phone Number | 1 (985) 276-7786 |
| Is this project complete? | No |
| Is this account ready to be closed? | No |
| Amount Awarded | $14,780 |
| Amount Spent | $0 |
| Purpose | This was funded to install a Type I and a Type II RO water systems at the Hill Farm Teaching facility for teaching horticultural and related courses that requires water treatments for lab activities. |
| Benefits Demographics | We estimated that this project, upon completion, will benefit a total of 8 courses and 260 students and other end-users. |
| Comments | We are grateful and really appreciate that this project was selected for funding. We experienced significant delays due to the communications needed with the manufacture on a correct quotation for both systems, required infrastructure changes for appropriate wall installation of the Type I system in the classroom, and in addition, the Type II system originally planned to be installed outside is now recommended by the manufacture to be installed inside with pipes extending to the outside area where it is needed with winter protection. We are close to completion of the project with these pipes being installed recently. |
| Justification (if an extension is requested) | We now have the correct quotation and the conditions that meet installation requirements and would like to request for an extension to finish the project before September 30th, 2026. |