| Project ID | PJ001232 |
| --- | --- |
| Project Fiscal Year | 2025-2026 |
| College/Department/Unit | LSU Libraries |
| Title of Project | Expanding the LSU Libraries Creator Space. |
| Name of Principle Implementor | Michael Stewart / (Gina Costello, Co-PI) |
| Email | gcoste1@lsu.edu |
| Phone Number | (225) 578-2217 |
| Is this project complete? | No |
| Is this account ready to be closed? | No |
| Amount Awarded | $51,171 |
| Amount Spent | $38,870 |
| Justification (if an extension is requested) | As part of the ITS Centralization Project, Michael Stewart (PI) has moved to a position entirely outside the Libraries as of May 15, 2026. He will not have any involvement in this project after May 15. Another staff member will be helping Co-PI Gina Costello with the remaining grant work. This personnel change will delay our ability to complete certain parts of the project, so we request a 1-semester extension. Along with the extension, we request that Co-PI Gina Costello be made the sole PI and that Michael Stewart be removed from the project. |