| Project ID | PJ001233 LSUAM ¦ STF26 - |
| --- | --- |
| Project Fiscal Year | 2025-2026 |
| College/Department/Unit | College of Art and Design, Digital Art |
| Title of Project | Digital Human Initiative - Building a National Platform for Performance, Health, and Simulation |
| Name of Principle Implementor | Christine Bruening |
| Email | cbruening@lsu.edu |
| Phone Number | 18143575247 |
| Is this project complete? | No |
| Is this account ready to be closed? | No |
| Amount Awarded | $102,924 |
| Amount Spent | $0 |
| Equipment | Photogrametry Rig |
| Purpose | Facilitate the creation of student athlete avatars for injury recovery/prevention research collaboration between Kinesiology , LSU Athletics, Computer Science, Bioengineering and Digital Art. |
| Benefits Demographics | Students Faculty and Staff in the following departments: Bioengineering, Digital Art, Digital Media Art and Engineering, Kinesiology, Computer Science, Fashion and Textiles. |
| Justification (if an extension is requested) | We tried to circumvent the bidding process by acquiring our equipment through a master contractor, as we needed to confirm whether we had secured another grant to help fund this purchase. Unfortunately, each time we began the onboarding process with one of the Master Contracts, we encountered issues. It now appears that we will have to enter the bidding process, which delays us by about a month. Given that the lead time for ordering this equipment is seven weeks, it seems we will require an extension, as the equipment is unlikely to arrive by the June 30th deadline. |